## Slide 1: Quantifying immediate cost savings and long-term structural value through self-performing freight – Phase 2 Team Charter

## Slide 2: The project charter covers project objectives, KPIs, stakeholders, and cadence — anchored in an agile, sprint-based implementation approach
The objective of this project is to optimize Diverzify’s freight and logistics operations by transitioning to a self-performing freight model in partnership with Xpress Global Systems (XGS). This initiative is structured into two distinct phases
Project Overview
Sprint Objectives
Onboard EVP with the new freight strategy through structured, interactive sessions
Collaborate with site teams to co-develop and validate pilot strategies tailored to local needs
Establish baseline metrics for freight cost, class adherence, and shipment performance per site prior to rollout
Equip relevant stakeholders (EVP, ops teams, salesforce users) with the training and documentation to sustain the new freight logic and tools
Develop mechanisms for surfacing and resolving edge cases or misclassifications during early rollouts
Integrate optimized freight costing into IFS and Salesforce through incremental system enhancements
Deliver measurable XGS savings for the Top 10 sites using data-driven sprints and continuous feedback loops
Develop and implement a dashboard for monitoring freight policy adherence and shipment tracking
Baseline data documented for 100% of rollout sites
Data reviewed and validated with EVPs
100% of target user training manual developed
100% of all data edge cases resolved in 4-weeks
Freight logic active an operational in both systems for pilot sites
Dashboard live and accessible by the end of sprint
Key measures of success (KPIs)
Project management support: Assists project manger in executing project goals
Project Governance
Analysis and Modelling — This phase involved a comprehensive assessment of Diverzify’s freight data, rate structures, and logistics patterns. A data-driven freight model was developed to identify cost-saving opportunities and optimize route performance
Implementation and Roll-Out — This charter supports the launch of the second phase, which will operationalize the findings from Phase 1 across Diverzify’s top 10 sites. The implementation will be led by a joint working group comprising team members from Africa International Advisors (AIA) and Diverzify.
Project Management: Defines project goals and facilitate team meetings
Cadence
Steercom Cadence
Team : AIA – Diverzify
Working com Cadence
Team: Divezify – IT support
Daily stand-up with working committee and weekly check-ins with steering committee
Continuous improvement check-in to discuss what went wrong and action items for process improvement
Agile Methods

## Slide 3: Sprint milestones and deliverables are distributed across the project team
Sprint | Milestone | Linked Objective | Project team
Sprint 1 | EVP onboarding session completed + materials signed off | EVP Onboarding | Diverzify
Sprint 2 | Site-specific pilot templates designed and distributed | Pilot Strategy Co-Design | AIA - Diverzify
Sprint 3 | IFS integration test environment live with optimized freight logic | System Integration | AIA - Diverzify
Sprint 4 | Salesforce quoting logic tested and refined | System Integration | AIA - Diverzify
Sprint 5 | Dashboard MVP (tracking cost, class compliance) deployed | Compliance & Tracking | AIA- Diverzify
Sprint 6 | Site 1–3 rollout of XGS freight costing logic | XGS Savings at Top 10 | AIA- Diverzify
Sprint 7 | Post-rollout feedback loop + corrective actions from Sites 1–3 | Exception Handling | AIA - Diverzify
Sprint 8 | Final 7 site rollouts and baseline-to-actual savings comparison | XGS Savings Realization | AIA - Diverzify
Sprint 9 | Training completion for all users + adoption metrics collected | Change Management | Diverzify
Sprint 10 | Final dashboard version + transition to BAU monitoring | Compliance & Long-Term Oversight | AIA - Diverzify
Onboard EVP with the new freight strategy through structured, interactive sessions
Collaborate with site teams to co-develop and validate pilot strategies tailored to local needs
Establish baseline metrics for freight cost, class adherence, and shipment performance per site prior to rollout
Integrate optimized freight costing into IFS (OH) and Salesforce (market) through incremental system enhancements
Develop mechanisms for surfacing and resolving edge cases or misclassifications during early rollouts
Equip stakeholders with the training and documentation to sustain the new freight logic and tools
Develop and implement a dashboard for monitoring freight policy adherence and shipment tracking
Implementation Objective
Sprint planning and milestones linked to implementation objective
Establish a unified UOM structure for all inventory data to support accurate freight modeling and reporting

## Slide 4: Sprint milestones and deliverables are distributed across the project team
Sprint | Milestone | Linked Objective | Project team
Sprint 1 | EVP onboarding session completed + materials signed off | EVP Onboarding | Diverzify
Sprint 2 | Site-specific pilot templates designed and distributed | Pilot Strategy Co-Design | AIA - Diverzify
Sprint 3 | Data cleaning and preparation | System Integration | AIA - Diverzify
Sprint 4 | IFS integration test environment live with optimized freight logic | System Integration | AIA - Diverzify
Sprint 4 | Salesforce quoting logic tested and refined | System Integration | AIA - Diverzify
Sprint 5 | Dashboard MVP (tracking cost, class compliance) deployed | Compliance & Tracking | AIA- Diverzify
Sprint 6 | Site 1–3 rollout of XGS freight costing logic | XGS Savings at Top 10 | AIA- Diverzify
Sprint 7 | Post-rollout feedback loop + corrective actions from Sites 1–3 | Exception Handling | AIA - Diverzify
Sprint 8 | Final 7 site rollouts and baseline-to-actual savings comparison | XGS Savings Realization | AIA - Diverzify
Sprint 9 | Training completion for all users + adoption metrics collected | Change Management | Diverzify
Sprint 10 | Final dashboard version + transition to BAU monitoring | Compliance & Long-Term Oversight | AIA - Diverzify
Onboard EVP with the new freight strategy through structured, interactive sessions
Collaborate with site teams to co-develop and validate pilot strategies tailored to local needs
Establish baseline metrics for freight cost, class adherence, and shipment performance per site prior to rollout
Integrate optimized freight costing into IFS (OH) and Salesforce (market) through incremental system enhancements
Develop mechanisms for surfacing and resolving edge cases or misclassifications during early rollouts
Equip stakeholders with the training and documentation to sustain the new freight logic and tools
Develop and implement a dashboard for monitoring freight policy adherence and shipment tracking
Implementation Objective
Sprint planning and milestones linked to implementation objective
Establish a unified UOM structure for all inventory data to support accurate freight modeling and reporting

## Slide 5
Thank you